## Overview
Multi-Agent Finance / Risk Analysis
Current features + 1-month improvement roadmap (4 h/day) + vulnerability / scalability review
Generated 2026-07-04 • LangGraph + Flask + React • AWS ECS Express Mode (Fargate+ALB) / S3+CloudFront
Capacity: 4 h/day × 5 days × 4 weeks = 80 h. Month-1 = 13 initiatives at exactly 80 h. To fit, N5 (cost cut) moved to Phase-2; I2 dropped (secrets already managed).
Vulnerability & scalability POVs cross-checked with Gemini; IAM/secrets items re-verified against the actual repo.
Tab | What it contains
Current Features | Everything implemented today, grouped by subsystem, with a status flag.
Improvement Plan | Month-1 initiatives (hours + week) that fit 80 h, then a Phase-2 backlog.
Vulnerability POV | Security review: attack surface, severity, mitigation, linked plan ID.
Scalability POV | Bottlenecks (incl. cost + UI perf) and how to scale each tier.
Gantt | 4-week timeline (4 h/day); each cell = hours that week; weekly load vs 20 h; Why/How per row.
Milestones | M0-M4 checkpoints with target dates + a diamond-marker timeline.
Legend
Implemented / Month-1
Partial
Stub / missing
Backlog / new

## Current Features
Current Features (implemented state)
# | Subsystem | Feature | Status | Notes / file
1 | Orchestration | Chain: data → (sentiment ‖ valuation ‖ fundamental) → risk → writer; parallel fan-out writes disjoint keys | Implemented | src/main.py build_chain_graph()
2 | Orchestration | Debate: debate_manager hub; route_debate → lowest-turn specialist; consensus or agent_max_turn(5) | Implemented | build_final_recommendation_graph()
3 | Agents | Six specialists: data, sentiment, valuation, fundamental, risk, writer | Implemented | src/agents.py
4 | Agents | Debate specialists supervised by debate_manager | Implemented | src/debate_agents.py
5 | Agents | Sentiment & fundamental = create_react_agents w/ constrained structured output | Implemented | schemas.py, agents.py
6 | Agents | Keyword sentiment scorer | Stub | Returns 'neutral' — tools.py:385
7 | Agents | Synthetic news fallback when no POLYGON_API_KEY | Partial | tools.py _generate_synthetic_news
8 | Backend API | Read/enqueue endpoints + legacy POST /api/analyze; 202+job else 200+snapshot | Implemented | backend/app.py
9 | Backend API | Watchdog ANALYZE_TIMEOUT_SECS(900); gunicorn gthread serving | Implemented / New | Dockerfile.backend
10 | Worker | Serial loop: claim_next_job (FOR UPDATE SKIP LOCKED) → run_pipeline_for_horizon | Implemented | src/worker.py
11 | Worker | Idle stale-refresh sweep + weekly EDGAR filing sweep | Implemented | snapshots.py, edgar_ingest.py
12 | Snapshots | Horizon presets SHORT/MID/LONG; append-only snapshots; jobs table + partial unique index | Implemented | horizons.py, db.py
13 | RAG | Filings in Postgres+pgvector; query_10k_documents cosine search; embedding-model namespacing | Implemented | rag_utils.py, tools.py:439
14 | RAG | SEC EDGAR auto-ingest (on-demand + weekly); text archived to FILINGS_RAW_DIR | Implemented | edgar_ingest.py
15 | LLM | Provider auto-select OpenAI→Anthropic→Google→Ollama→MockLLM; embeddings abstraction | Implemented | config.py
16 | Tools | Price (Polygon+yfinance fallback), news (Polygon+scrape), compute_risk, compute_valuation_metrics | Implemented | tools.py
17 | Frontend | React app; useAllSnapshots 3-horizon fan-out polling + transient-blip tolerance | Implemented / New | useAllSnapshots.js
18 | Frontend | Failed-job UX + retry(); run/risk history views | Implemented | frontend/
19 | Reporting | Writer renders fixed Markdown template (+debate consensus) → PDF | Implemented | agents.py writer
20 | Testing/Eval | Integration test (rec vs realised delta); eval suite (struct-output, grounding, stability) | Implemented | tests/, evals/
21 | Deploy | Docker; AWS ECS Express Mode (Fargate+ALB), S3/CloudFront; secrets in Secrets Manager; apex via Cloudflare | Implemented | AWS_DEPLOYMENT.md

## Improvement Plan
Improvement Plan — Month 1 (4 h/day, 80 h) + Backlog
Month-1 rows are scheduled in the Gantt. Effort(h) sums to 80. Backlog = Phase 2 (beyond month 1).
ID | Initiative | Category | Priority | Effort(h) | Week | Status | Description / outcome
N10 | Refactor create_react_agent → create_agent | Architecture | P2 | 8 | W1 | Month1 | Migrate sentiment/fundamental/debate agents to the current create_agent API; bump langgraph/langchain versions; re-run integration + eval suites. Done FIRST so N4's MCP tools wire into the migrated agent. [user]
N4 | Add complementary SEC EDGAR MCP server (XBRL) | Architecture | P2 | 10 | W1 | Month1 | RAG gives narrative but not reliable exact numbers; add a self-hosted SEC EDGAR MCP server (exact XBRL financials, tagged by concept/period) as a NEW fundamental-agent tool alongside query_10k_documents. Complements the RAG, doesn't replace it. Vet the community server (e.g. cyanheads / stefanoamorelli). [user]
N9 | Model indicator on UI | Product/UX | P2 | 2 | W1 | Month1 | Show which provider/model produced a result (GPT-4o / Ollama / Bedrock / Mock) so users can gauge trust. Backend already resolves it (_detect_model_provider). [user]
N6 | Reject non-SEC tickers at front door | Reliability | P1 | 4 | W2 | Month1 | ✅ IMPLEMENTED. Front-door validation: reject symbols that aren't recognized SEC filers BEFORE a job is created. _resolve_snapshot + a GET /api/ticker/<t> endpoint return 404 for unknown tickers (checked vs SEC's cached ticker→CIK map, fail-open if SEC is down); the Landing search validates on submit and shows an inline error. Real filers with no recent 10-K/10-Q still run (fundamental → N/A). [user]
I20 | Fail-closed on degraded LLM | Reliability | P1 | 4 | W2 | Month1 | Never persist MockLLM/fallback output as a valid snapshot — mark the run degraded. [Gemini]
I19 | CI → GitHub OIDC + scoped Bedrock task role | Security | P1 | 4 | W2 | Month1 | No s3:*/rds:* wildcards exist today (verified). Real gaps: CI uses long-lived IAM-user static keys → GitHub OIDC + short-lived role; N3 needs a bedrock:InvokeModel-only task role.
N3 | Add AWS Bedrock as LLM provider | Data/LLM | P2 | 6 | W2 | Month1 | Add Bedrock to config.py get_llm(); keeps inference inside your AWS account/region. [user]
I1 | API auth + rate limiting | Security | P0 | 10 | W2-W3 | Month1 | Add API-key/JWT auth + a rate limiter on enqueue so nobody can spam expensive jobs (cost+DoS).
I8 | pgvector ANN index (HNSW) | Scalability | P1 | 3 | W3 | Month1 | Add an approximate index so filing retrieval stops full-scanning as the corpus grows.
N8 | Running-job indicator on home page | Product/UX | P1 | 4 | W3 | Month1 | After returning to the home/list page the user has no signal a job is still running; add a persistent banner/badge fed by a list-active-jobs endpoint. [user]
N1 | Frontend improvements | Product/UX | P2 | 5 | W3 | Month1 | General UI polish: layout, states, responsiveness, clearer horizon/recommendation presentation. [user]
N7 | Fix UI lag (stock graphs) | Product/UX | P1 | 8 | W4 | Month1 | Lazy-load/memoize charts, downsample series, cache price history client-side; kill the graph-load jank. [user]
N2 | Add public-analyzer insights | Quality/Product | P2 | 12 | W4 | Month1 | Surface metrics like public stock analyzers: valuation ratios, momentum/technical signals, peer comparison, analyst-style summary. [user]
N5 | Cut cost (ECS Express → cheaper) | Cost | P1 | - | - | Backlog | ECS Express Mode is pricey for steady low traffic: plain Fargate + Fargate Spot, scale-to-zero, App Runner/Lambda for spiky parts, VPC endpoints. Deferred to Phase-2 per user. [user]
I3 | Lock down CORS + error responses | Security | P1 | - | - | Backlog | Restrict CORS to frontend origin; stop leaking raw exception text to clients.
I4 | Prompt-injection hardening | Security | P1 | - | - | Backlog | Treat filing chunks + scraped news as untrusted; delimit in prompts; validate debate outputs.
I5 | SSRF guard on article fetching | Security | P2 | - | - | Backlog | Scheme/host allowlist; block private IPs before fetching Polygon URLs.
I6 | Concurrent workers + autoscale | Scalability | P1 | - | - | Backlog | N worker replicas (SKIP-LOCKED safe) autoscaled on queue depth. Ties into N5.
I7 | Postgres connection pooling | Scalability | P1 | - | - | Backlog | pgbouncer to remove per-call connect + retry-backoff stalls.
I9 | Snapshot read caching / CDN TTL | Scalability | P2 | - | - | Backlog | Short-TTL cache on GET /api/snapshot to absorb the poll fan-out.
I11 | Real sentiment model | Quality/Eval | P1 | - | - | Backlog | Replace the 'neutral' stub with a finance classifier / LLM scoring.
I12 | Expand evals + CI gate | Quality/Eval | P1 | - | - | Backlog | Grounding + stability metrics in CI; fail on regression.
I13 | Observability (metrics/traces) | Observability | P1 | - | - | Backlog | Per-agent latency/cost, LangSmith in prod, dashboards + alerts.
I14 | LLM cost / rate controls | Scalability | P2 | - | - | Backlog | Response caching, cheaper sub-step models, concurrency caps.
I15 | Async filing + news I/O | Reliability | P2 | - | - | Backlog | Move ensure_filings + synchronous scraping off the pipeline critical path. [Gemini]
I16 | LLM narrative report + disclaimer | Product/UX | P3 | - | - | Backlog | Grounded citation-checked writeup; add 'not financial advice' disclaimer.
I17 | Backtest / accuracy dashboard | Product/UX | P3 | - | - | Backlog | Historical recommendation-vs-outcome accuracy per horizon.
I18 | CI/CD + IaC | Reliability | P2 | - | - | Backlog | Terraform/CDK the stack; automated build→deploy; staging env.
Month-1 total |  |  |  | 80

## Vulnerability POV
Vulnerability / Security POV
Severity = likelihood × impact for a public AWS deployment.
# | Area | Current state / risk | Severity | Recommended mitigation | Plan ID
1 | API auth | No auth on /api/* — anyone reaching the ALB can enqueue expensive LLM jobs. | High | Auth + rate limiting on enqueue. | I1
2 | Secrets | AWS runtime secrets already in Secrets Manager; .env is gitignored + not in the image (verified). Only a local Gemini MCP key (session-scoped) needs rotating. | Low (resolved) | Rotate the exposed Gemini key; no project change needed. | —
3 | DoS / cost | No rate limit/quota; one client can exhaust worker + LLM budget. | High | Per-key quotas; backpressure. | I1,I6
4 | Prompt injection | Retrieved 10-K chunks + scraped news feed straight into agent prompts. | Medium | Delimit/untrust external text; validate outputs. | I4
5 | SSRF | Article-URL fetching can reach internal network / metadata. | Medium | Scheme/host allowlist; block private IPs. | I5
6 | CORS | Flask-CORS likely permissive. | Medium | Restrict to frontend origin. | I3
7 | Info leakage | Raw exception text surfaced via job.error. | Low-Med | Generic client errors; detail to logs. | I3
8 | Dependencies | newspaper3k / yfinance / curl_cffi supply-chain risk. | Medium | Pin + scan (pip-audit); drop unused. | I18
9 | Data integrity | Fallback ends in MockLLM — dummy output could be stored as a valid snapshot. | High | Fail closed; never persist mock output. [Gemini] | I20
10 | IAM / cloud | No over-broad task role today; but CI uses long-lived IAM-user static keys, and Bedrock (N3) will need a new task role. | Medium | CI → GitHub OIDC; scoped bedrock:InvokeModel task role. | I19
11 | Data egress | Ticker/document context sent to 3rd-party LLMs. | Med (legal) | Prefer Bedrock/local for sensitive input; review retention. [Gemini] | N3
12 | Cost DoS (agents) | Flawed debate loop could burn spend — bounded by agent_max_turn(5)+recursion_limit(100). | Low-Med (mitigated) | Keep caps; add per-run cost ceiling + alert. [Gemini] | I13
13 | Compliance | Buy/hold/sell output needs a 'not financial advice' disclaimer. | Med (legal) | Disclaimer in UI + report. | I16

## Scalability POV
Scalability POV
Where the system bottlenecks as tickers, horizons, users — and cost — grow.
# | Tier | Current limit / bottleneck | Impact at scale | Recommended move | Plan ID
1 | Worker | Single serial process; one job (minutes) at a time. | Queue backs up with many tickers/horizons. | Multiple replicas + autoscale on queue depth. | I6
2 | Postgres | New connection per call w/ retry-backoff; no pooling. | Connection storms; multi-second stalls. | pgbouncer; read replica; size up RDS. | I7
3 | Vector search | Cosine search likely without an ANN index. | Retrieval latency grows with chunk count. | HNSW index. | I8
4 | API read path | 3 horizons × ~3s polling × N users. | Fine for hundreds; bites only at thousands concurrent. [Gemini] | gunicorn threads (done) + short-TTL/CDN cache. | I9
5 | LLM provider | Many agent calls + debate rounds per run; RPM/cost caps. | Throttling + spend at volume. | Caching, cheaper sub-step models, concurrency caps; Bedrock option. | I14,N3
6 | Filing/news I/O | ensure_filings + synchronous scraping inside pipeline. | Worker blocked on I/O — starvation. [Gemini] | Async fetch / dedicated scrape service. | I15
7 | Snapshots table | Append-only, unbounded growth. | History queries slow over time. | Composite index + retention. | I10/I12
8 | Cost / infra | ECS Express Mode convenience pricing high for steady low traffic. | Monthly spend disproportionate to load. | Plain Fargate + Fargate Spot, scale-to-zero, right-size; App Runner/Lambda for spiky parts. [user] | N5
9 | Frontend perf | Stock-graph rendering + price-history load cause UI lag. | Poor UX on graph-heavy views. [user] | Lazy-load/memoize charts, downsample, client cache, paginate. | N7
10 | Network egress | ECS ↔ S3/RDS + outbound via NAT Gateway. | NAT data-processing cost + throttling. [Gemini] | VPC endpoints for S3/RDS. | N5,I18

## Gantt
Roadmap Gantt — 1 month, 4 h/day (20 h/week)
Each cell = hours worked that week. Cell colour = category. Bottom row checks weekly load vs 20 h. Why/How per row.
Initiative | W1 | W2 | W3 | W4 | Total h | Why | How
N10 Refactor → create_agent | 8 |  |  |  | 8 | LangGraph's create_react_agent is superseded by create_agent; staying current avoids deprecation breakage and unlocks new features. Done FIRST so N4's MCP tools wire straight into the migrated agent. | Migrate the sentiment/fundamental/debate agents from create_react_agent to create_agent; bump langgraph/langchain in requirements.txt; re-run integration + eval suites to confirm structured output still works.
N4 Complementary SEC MCP (XBRL) | 10 |  |  |  | 10 | The RAG gives narrative but can't reliably return exact financials — filing tables are flattened by get_text(), retrieval is semantic, and the LLM paraphrases (the number-grounding eval exists precisely for this). A self-hosted SEC EDGAR MCP server returns exact XBRL numbers (revenue/EPS/margins, tagged by concept/period), complementing the RAG's qualitative half — not replacing it. | Self-host a vetted SEC EDGAR MCP server (e.g. cyanheads/secedgar-mcp-server — stdio now, HTTP sidecar later — or stefanoamorelli/sec-edgar-mcp); add langchain-mcp-adapters; load its XBRL/company-facts tools as LangChain tools and give them to the fundamental agent ALONGSIDE query_10k_documents, behind a flag. Builds on N10 (refactored agent). Vet the community server before depending on it.
N9 Model indicator on UI | 2 |  |  |  | 2 | Users can't tell which model produced a result (GPT-4o vs Ollama vs Bedrock vs Mock) — hurts trust and debugging. | Expose the resolved provider/model (backend already has _detect_model_provider) via the API; render a small badge on results / header.
N6 Reject non-SEC tickers (front door) |  | 4 |  |  | 4 | ✅ IMPLEMENTED. Enqueuing a full multi-agent + debate run for a typo / non-existent symbol wastes minutes of compute + LLM spend. Rejecting at the front door (not mid-pipeline) means no doomed job is ever created. | Validate the ticker against SEC's cached ticker→CIK map: _resolve_snapshot returns 404 before enqueue (the sole enqueue path) + a GET /api/ticker/<t> endpoint the Landing search calls before navigating; fail-open if SEC is unreachable. Valid filers lacking filings still run (empty fundamental).
I20 Fail-closed on degraded LLM |  | 4 |  |  | 4 | The provider chain falls back to MockLLM; dummy output could be stored as a real snapshot = silent fake analysis. | Detect a Mock/degraded provider; mark the run 'degraded', skip persisting it as a valid snapshot, and surface the state in the UI.
I19 CI→OIDC + Bedrock task role |  | 4 |  |  | 4 | Verified against the repo: no s3:*/rds:* wildcards exist (no app task role; exec role scoped to 3 secret ARNs). Real gaps are static IAM-user keys in CI and the task role Bedrock (N3) will need. | Replace GitHub static AWS keys with GitHub OIDC → a short-lived assumed deploy role (trust scoped to this repo); when N3 lands, attach a task role granting only bedrock:InvokeModel on the specific model ARNs.
N3 Add AWS Bedrock provider |  | 6 |  |  | 6 | Keeps inference inside your AWS account/region (less data egress to external SaaS LLMs) and adds provider redundancy. | Add a Bedrock branch to config.py get_llm() (bedrock-runtime, e.g. Claude on Bedrock); select via MODEL_PROVIDER; keep OpenAI fallback.
I1 API auth + rate limiting |  | 2 | 8 |  | 10 | Open /api/* lets anyone enqueue minutes-long LLM jobs → cost blowup + DoS. | Add API-key/JWT auth middleware in Flask + a per-key rate limiter/quota on the enqueue endpoints; reject unauthenticated calls.
I8 pgvector HNSW index |  |  | 3 |  | 3 | Without an index every RAG query full-scans filing_chunks (O(n)); retrieval slows as more filings are ingested. | CREATE INDEX ... USING hnsw (embedding vector_cosine_ops); keep the ticker/date + embedding-model filters; tune m / ef_search.
N8 Running-job indicator (home) |  |  | 4 |  | 4 | After enqueuing a job and returning to the home/list page, the user gets no signal analysis is still running — looks like nothing happened. | Add a backend endpoint listing active (queued/running) jobs; show a persistent banner/badge on the home page that polls it and links to the in-progress ticker; clear when ready.
N1 Frontend improvements |  |  | 5 |  | 5 | General UX polish improves clarity of horizons/recommendations and perceived quality. | Refine layout, loading/empty/error states, responsiveness, and clearer horizon + BUY/HOLD/SELL presentation.
N7 Fix UI lag (stock graphs) |  |  |  | 8 | 8 | Chart rendering + price-history loading cause visible UI jank, worst on graph-heavy views. | Lazy-load/memoize chart components, downsample long series, cache price history client-side, paginate/virtualize; profile with React DevTools.
N2 Public-analyzer insights |  |  |  | 12 | 12 | Users expect the metrics they see on public stock analyzers; adds real decision value. | Compute/display valuation ratios, momentum/technical signals, peer comparison and an analyst-style summary; surface in report + UI.
Weekly load (h) | 20 | 20 | 20 | 20 | 80
Capacity (4h×5d) | 20 | 20 | 20 | 20 | 80
Category legend
Architecture
Product/UX
Reliability
Security
Data/LLM
Scalability
Quality/Product

## Milestones
Milestone Chart — 1 month (4 h/day)
Key checkpoints (deliverable completions), not durations. Diamonds mark the target week. Start: Mon 2026-07-06.
ID | Milestone | Target date | Week | Key deliverables | Status | Track
M0 | Kickoff / baseline | 2026-07-06 | Start | Plan locked; environments + secrets access ready | Planned | Reliability
M1 | Agent refactor + SEC MCP | 2026-07-10 | W1 | N10 create_react_agent→create_agent, N4 SEC EDGAR MCP (exact XBRL financials) alongside RAG, N9 model indicator | Planned | Architecture
M2 | Reliability + security + Bedrock | 2026-07-17 | W2 | N6 reject non-SEC tickers (done), I20 fail-closed, I19 CI→OIDC, N3 Bedrock provider; API auth (I1) started | Planned | Security
M3 | Scale + auth + UX | 2026-07-24 | W3 | I8 HNSW index, I1 auth+rate-limit done, N8 running-job indicator, N1 frontend polish | Planned | Product/UX
M4 | UI perf + insights → Month-1 done | 2026-07-31 | W4 | N7 stock-graph lag fix, N2 public-analyzer insights | Planned | Product/UX
Timeline
Milestone | W1 07/10 | W2 07/17 | W3 07/24 | W4 07/31
M1 Agent refactor + SEC MCP | ◆ M1
M2 Reliability + security + Bedrock |  | ◆ M2
M3 Scale + auth + UX |  |  | ◆ M3
M4 UI perf + insights → Month-1 done |  |  |  | ◆ M4
Track legend
Security
Cost
Architecture
Product/UX
Reliability
Data/LLM